# PlayArena Elite - 30-Day Completion Plan

## Project Overview

**Goal:** Complete all PRD requirements using hybrid approach (Django templates + REST API)

**Timeline:** 30 days

**Approach:** Keep existing Django templates, add REST API layer, complete missing features

---

## Phase Breakdown

### **Week 1 (Days 1-7): Foundation & Critical Infrastructure**

### **Week 2 (Days 8-14): Payment Integration & Evidence System**

### **Week 3 (Days 15-21): API Layer & Security**

### **Week 4 (Days 22-28): Testing, Polish & Deployment**

### **Days 29-30: Final Testing & Launch**

---

## Detailed Daily Plan

### **WEEK 1: Foundation & Critical Infrastructure**

#### **Day 1: Project Setup & Database Migration**

**ðŸ”§ BACKEND TASKS:**

- [ ] Set up PostgreSQL database (local + production config)

- [ ] Install PostgreSQL dependencies (`psycopg2-binary`)

- [ ] Update `settings.py` with PostgreSQL configuration

- [ ] Create database migration scripts

- [ ] Migrate existing SQLite data to PostgreSQL

- [ ] Test database connection and queries

- [ ] Set up environment variables (`.env` file)

- [ ] Move hardcoded secrets to environment variables

- [ ] Install `python-decouple` or `django-environ`

**ðŸŽ¨ FRONTEND TASKS:**

- [ ] No frontend tasks for Day 1

**ðŸ“¦ DELIVERABLES:**

- PostgreSQL database running

- Environment variables configured

- All secrets moved from code

**â±ï¸ TIME ESTIMATE:** 6-8 hours

---

#### **Day 2: Security Hardening**

**ðŸ”§ BACKEND TASKS:**

- [ ] Install and configure `django-ratelimit` for rate limiting

- [ ] Add rate limiting to authentication endpoints

- [ ] Add rate limiting to wallet operations

- [ ] Install and configure `django-cors-headers` for API

- [ ] Set up security headers (CSP, XSS protection)

- [ ] Configure password validators (strength requirements)

- [ ] Review and fix any SQL injection vulnerabilities

- [ ] Add input sanitization helpers

**ðŸŽ¨ FRONTEND TASKS:**

- [ ] Add CAPTCHA to registration/login forms (optional but recommended)

- [ ] Update forms to show password strength indicators

**ðŸ“¦ DELIVERABLES:**

- Rate limiting active on critical endpoints

- Security headers configured

- Enhanced password validation

**â±ï¸ TIME ESTIMATE:** 5-6 hours

---

#### **Day 3: Wallet Deposit/Withdrawal Backend**

**ðŸ”§ BACKEND TASKS:**

- [ ] Create `Deposit` model (amount, status, payment_method, transaction_id)

- [ ] Create `Withdrawal` model (amount, status, payment_method, account_details)

- [ ] Create deposit view with payment gateway integration (Stripe/PayPal/Mobile Money)

- [ ] Create withdrawal view with validation

- [ ] Add deposit/withdrawal status tracking

- [ ] Implement wallet balance integrity checks

- [ ] Add transaction reconciliation helper functions

- [ ] Create admin views for deposit/withdrawal management

- [ ] Add webhook handlers for payment confirmations

**ðŸŽ¨ FRONTEND TASKS:**

- [ ] No frontend tasks for Day 3

**ðŸ“¦ DELIVERABLES:**

- Deposit/withdrawal models and views

- Payment gateway integration started

- Balance integrity checks

**â±ï¸ TIME ESTIMATE:** 7-8 hours

---

#### **Day 4: Wallet UI Implementation**

**ðŸ”§ BACKEND TASKS:**

- [ ] Create deposit URL routes

- [ ] Create withdrawal URL routes

- [ ] Create deposit/withdrawal view functions

- [ ] Add form validation logic

**ðŸŽ¨ FRONTEND TASKS:**

- [ ] Create `wallet/deposit.html` template

- [ ] Create `wallet/withdraw.html` template

- [ ] Create `wallet/transaction_history.html` template (enhanced)

- [ ] Add deposit form with payment method selection

- [ ] Add withdrawal form with account details

- [ ] Update dashboard to link "Add Funds" and "Withdraw" buttons

- [ ] Add deposit/withdrawal status display

- [ ] Style wallet pages to match existing design

- [ ] Add JavaScript for form validation and payment processing

**ðŸ“¦ DELIVERABLES:**

- Complete wallet deposit/withdrawal UI

- Functional payment forms

- Enhanced transaction history

**â±ï¸ TIME ESTIMATE:** 6-7 hours

---

#### **Day 5: Payment Gateway Integration (Part 1)**

**Tasks:**

- [ ] Choose payment provider (Stripe recommended for cards, add Mobile Money API)

- [ ] Set up payment provider account and API keys

- [ ] Install payment SDK (e.g., `stripe`, `paystack`, etc.)

- [ ] Create payment service class/module

- [ ] Implement deposit payment processing

- [ ] Implement payment webhook handler

- [ ] Test payment flow (sandbox/test mode)

- [ ] Add payment status callbacks

- [ ] Create payment transaction records

**Deliverables:**

- Payment gateway integrated

- Deposit payments working (test mode)

- Webhook handlers functional

**Time Estimate:** 7-8 hours

---

#### **Day 6: Payment Gateway Integration (Part 2)**

**Tasks:**

- [ ] Implement withdrawal processing

- [ ] Add withdrawal validation (minimum amounts, limits)

- [ ] Integrate withdrawal API (if provider supports)

- [ ] Create withdrawal approval workflow (manual or automated)

- [ ] Add payment method management (save cards, accounts)

- [ ] Test complete payment flow end-to-end

- [ ] Handle payment failures and retries

- [ ] Add payment notifications to users

**Deliverables:**

- Complete payment integration

- Withdrawal processing functional

- Payment notifications working

**Time Estimate:** 6-7 hours

---

#### **Day 7: Evidence Upload System (Backend)**

**Tasks:**

- [ ] Install and configure file storage (AWS S3, Cloudinary, or local)

- [ ] Add `evidence_file` field to `MatchResult` model

- [ ] Create `Evidence` model (match, user, file, file_type, uploaded_at)

- [ ] Create file upload view with validation

- [ ] Add file size limits (e.g., 10MB for images, 50MB for videos)

- [ ] Add file type validation (images: jpg, png; videos: mp4, mov)

- [ ] Implement file upload to storage

- [ ] Create evidence retrieval endpoints

- [ ] Add evidence display in dispute views

**Deliverables:**

- Evidence upload backend functional

- File storage configured

- Evidence model and views created

**Time Estimate:** 6-7 hours

---

### **WEEK 2: Payment Integration & Evidence System**

#### **Day 8: Evidence Upload UI**

**Tasks:**

- [ ] Add file upload field to match result submission form

- [ ] Create evidence upload UI component

- [ ] Add file preview functionality (images/videos)

- [ ] Add progress bar for file uploads

- [ ] Update `match_detail.html` to show evidence

- [ ] Create evidence gallery view

- [ ] Add evidence display in dispute detail page

- [ ] Style evidence upload components

- [ ] Add JavaScript for drag-and-drop upload (optional)

**Deliverables:**

- Evidence upload UI complete

- File preview working

- Evidence display in disputes

**Time Estimate:** 6-7 hours

---

#### **Day 9: Enhanced Match Result Submission**

**Tasks:**

- [ ] Update `submit_match_result` view to handle evidence

- [ ] Add evidence requirement validation (optional or required)

- [ ] Update match result display to show evidence

- [ ] Add evidence comparison in dispute views

- [ ] Create evidence review interface for support staff

- [ ] Add evidence download functionality

- [ ] Test evidence upload with various file types

- [ ] Add evidence deletion (for users before submission)

**Deliverables:**

- Evidence integrated into match results

- Support staff can review evidence

- Evidence validation working

**Time Estimate:** 5-6 hours

---

#### **Day 10: Dispute System Enhancements**

**Tasks:**

- [ ] Add evidence display to dispute detail page

- [ ] Create evidence comparison view (side-by-side)

- [ ] Add evidence notes/comments for support staff

- [ ] Enhance dispute resolution form with evidence review

- [ ] Add dispute pattern detection (flag users with frequent disputes)

- [ ] Create dispute statistics dashboard

- [ ] Add dispute escalation workflow

- [ ] Improve dispute notification messages

**Deliverables:**

- Enhanced dispute system with evidence

- Dispute pattern detection

- Better dispute workflow

**Time Estimate:** 6-7 hours

---

#### **Day 11: Logging & Monitoring Setup**

**Tasks:**

- [ ] Install and configure logging (Python `logging` module)

- [ ] Create audit log model (user, action, timestamp, details)

- [ ] Add audit logging to critical operations (wallet, matches, disputes)

- [ ] Set up error tracking (Sentry or similar)

- [ ] Configure log levels and handlers

- [ ] Create log rotation strategy

- [ ] Add monitoring dashboard (optional: Grafana)

- [ ] Set up email alerts for critical errors

**Deliverables:**

- Comprehensive logging system

- Error tracking configured

- Audit logs for financial operations

**Time Estimate:** 5-6 hours

---

#### **Day 12: Additional Games & Devices**

**Tasks:**

- [ ] Add NBA 2K to game choices

- [ ] Add Mortal Kombat to game choices

- [ ] Add console options (PlayStation, Xbox, PC) to device choices

- [ ] Update match creation form with new options

- [ ] Update match display to show new games/devices

- [ ] Test match creation with all new options

- [ ] Update landing page to showcase all games

- [ ] Add game-specific icons/images

**Deliverables:**

- All PRD games added

- Console/PC device support added

- UI updated for new options

**Time Estimate:** 4-5 hours

---

#### **Day 13: Reconciliation System**

**Tasks:**

- [ ] Create reconciliation job/management command

- [ ] Implement wallet balance verification (sum of transactions = balance)

- [ ] Add automatic discrepancy detection

- [ ] Create reconciliation report

- [ ] Add manual reconciliation interface for admins

- [ ] Set up scheduled reconciliation (daily cron job)

- [ ] Add reconciliation alerts for discrepancies

- [ ] Test reconciliation with various scenarios

**Deliverables:**

- Reconciliation system functional

- Automatic balance verification

- Admin reconciliation interface

**Time Estimate:** 6-7 hours

---

#### **Day 14: Week 2 Review & Bug Fixes**

**Tasks:**

- [ ] Review all Week 2 implementations

- [ ] Test payment flow end-to-end

- [ ] Test evidence upload/download

- [ ] Fix any bugs discovered

- [ ] Update documentation

- [ ] Code review and refactoring

- [ ] Performance testing

- [ ] Security review

**Deliverables:**

- All Week 2 features tested

- Bugs fixed

- Code reviewed

**Time Estimate:** 6-8 hours

---

### **WEEK 3: API Layer & Security**

#### **Day 15: Django REST Framework Setup**

**Tasks:**

- [ ] Install `djangorestframework` and dependencies

- [ ] Configure DRF in `settings.py`

- [ ] Set up API authentication (JWT tokens)

- [ ] Install `djangorestframework-simplejwt`

- [ ] Configure JWT settings

- [ ] Create API base URL structure (`/api/v1/`)

- [ ] Set up API permissions and throttling

- [ ] Create API documentation setup (Swagger/OpenAPI)

**Deliverables:**

- DRF installed and configured

- JWT authentication working

- API base structure created

**Time Estimate:** 5-6 hours

---

#### **Day 16: User & Authentication API**

**Tasks:**

- [ ] Create `UserSerializer` and `UserViewSet`

- [ ] Create `ProfileSerializer` and `ProfileViewSet`

- [ ] Create authentication endpoints (login, register, refresh token)

- [ ] Create password reset API endpoints

- [ ] Add user profile update endpoints

- [ ] Test authentication API with Postman/curl

- [ ] Add API documentation for auth endpoints

- [ ] Create API versioning structure

**Deliverables:**

- User authentication API complete

- Profile management API

- API documentation started

**Time Estimate:** 6-7 hours

---

#### **Day 17: Wallet API**

**Tasks:**

- [ ] Create `WalletSerializer` and `WalletViewSet`

- [ ] Create `TransactionSerializer` and `TransactionViewSet`

- [ ] Create deposit API endpoint

- [ ] Create withdrawal API endpoint

- [ ] Create transaction history API endpoint

- [ ] Add wallet balance endpoint

- [ ] Add API permissions (user can only access own wallet)

- [ ] Test wallet API endpoints

**Deliverables:**

- Complete wallet API

- Transaction API

- Secure wallet endpoints

**Time Estimate:** 6-7 hours

---

#### **Day 18: Match API**

**Tasks:**

- [ ] Create `MatchSerializer` and `MatchViewSet`

- [ ] Create `MatchResultSerializer` and `MatchResultViewSet`

- [ ] Create match creation API endpoint

- [ ] Create match joining API endpoint

- [ ] Create match list/filter API endpoints

- [ ] Create match detail API endpoint

- [ ] Create result submission API endpoint

- [ ] Add match cancellation API endpoint

- [ ] Test all match API endpoints

**Deliverables:**

- Complete match management API

- Result submission API

- Match filtering/search API

**Time Estimate:** 7-8 hours

---

#### **Day 19: Dispute & Messaging API**

**Tasks:**

- [ ] Create `DisputeSerializer` and `DisputeViewSet`

- [ ] Create dispute list API (for support staff)

- [ ] Create dispute detail API

- [ ] Create dispute resolution API

- [ ] Create `MessageSerializer` and `MessageViewSet`

- [ ] Create messaging API endpoints (send, list, conversation)

- [ ] Create notification API endpoints

- [ ] Add API permissions for support staff

- [ ] Test dispute and messaging APIs

**Deliverables:**

- Dispute management API

- Messaging API

- Notification API

**Time Estimate:** 6-7 hours

---

#### **Day 20: API Documentation & Testing**

**Tasks:**

- [ ] Set up Swagger/OpenAPI documentation

- [ ] Document all API endpoints

- [ ] Add request/response examples

- [ ] Create API test suite (using DRF test client)

- [ ] Test all API endpoints

- [ ] Create Postman collection

- [ ] Add API rate limiting

- [ ] Create API usage examples

**Deliverables:**

- Complete API documentation

- API test suite

- Postman collection

**Time Estimate:** 6-7 hours

---

#### **Day 21: API Security & Optimization**

**Tasks:**

- [ ] Review API security (authentication, permissions)

- [ ] Add API throttling per user

- [ ] Implement API versioning

- [ ] Add request/response validation

- [ ] Optimize API queries (select_related, prefetch_related)

- [ ] Add API caching where appropriate

- [ ] Review and fix N+1 query problems

- [ ] Performance testing for API endpoints

**Deliverables:**

- Secure and optimized API

- Performance improvements

- Security review complete

**Time Estimate:** 6-7 hours

---

### **WEEK 4: Testing, Polish & Deployment**

#### **Day 22: Comprehensive Testing (Backend)**

**Tasks:**

- [ ] Write unit tests for wallet operations

- [ ] Write unit tests for match creation/joining

- [ ] Write unit tests for result submission

- [ ] Write unit tests for dispute resolution

- [ ] Write unit tests for payment processing

- [ ] Write integration tests for complete workflows

- [ ] Test edge cases and error handling

- [ ] Run full test suite and fix failures

**Deliverables:**

- Comprehensive test coverage

- All tests passing

- Edge cases handled

**Time Estimate:** 7-8 hours

---

#### **Day 23: Frontend Testing & Polish**

**Tasks:**

- [ ] Test all frontend pages and forms

- [ ] Fix UI bugs and inconsistencies

- [ ] Improve error message display

- [ ] Add loading states for async operations

- [ ] Improve mobile responsiveness

- [ ] Test cross-browser compatibility

- [ ] Optimize CSS and JavaScript

- [ ] Add user feedback improvements

**Deliverables:**

- Polished frontend

- Mobile-responsive

- Cross-browser compatible

**Time Estimate:** 6-7 hours

---

#### **Day 24: Payment Integration Testing**

**Tasks:**

- [ ] Test deposit flow end-to-end (test mode)

- [ ] Test withdrawal flow end-to-end

- [ ] Test payment webhooks

- [ ] Test payment failures and retries

- [ ] Test multiple payment methods

- [ ] Verify payment transaction records

- [ ] Test payment notifications

- [ ] Prepare for production payment keys

**Deliverables:**

- Payment system fully tested

- Webhooks working correctly

- Ready for production

**Time Estimate:** 5-6 hours

---

#### **Day 25: Security Audit & Penetration Testing**

**Tasks:**

- [ ] Review all authentication flows

- [ ] Test for SQL injection vulnerabilities

- [ ] Test for XSS vulnerabilities

- [ ] Test CSRF protection

- [ ] Review file upload security

- [ ] Test rate limiting effectiveness

- [ ] Review API security

- [ ] Fix any security issues found

**Deliverables:**

- Security audit complete

- Vulnerabilities fixed

- Security best practices implemented

**Time Estimate:** 6-7 hours

---

#### **Day 26: Production Deployment Setup**

**Tasks:**

- [ ] Set up production server (AWS/GCP/Azure)

- [ ] Configure production database (PostgreSQL)

- [ ] Set up environment variables in production

- [ ] Configure production settings (DEBUG=False, etc.)

- [ ] Set up static file serving (S3/CloudFront)

- [ ] Configure media file storage (S3)

- [ ] Set up SSL certificates

- [ ] Configure domain and DNS

**Deliverables:**

- Production environment ready

- SSL configured

- Static/media files served correctly

**Time Estimate:** 6-8 hours

---

#### **Day 27: Deployment & Migration**

**Tasks:**

- [ ] Deploy application to production

- [ ] Run database migrations in production

- [ ] Migrate any existing data

- [ ] Configure production logging

- [ ] Set up monitoring and alerts

- [ ] Test production deployment

- [ ] Configure backup strategy

- [ ] Set up CI/CD pipeline (optional)

**Deliverables:**

- Application deployed to production

- Database migrated

- Monitoring active

**Time Estimate:** 7-8 hours

---

#### **Day 28: Final Testing & Bug Fixes**

**Tasks:**

- [ ] Complete end-to-end testing in production

- [ ] Test all user flows

- [ ] Fix any production bugs

- [ ] Performance testing in production

- [ ] Load testing (if possible)

- [ ] Final security check

- [ ] Update documentation

- [ ] Prepare launch checklist

**Deliverables:**

- Production-ready application

- All bugs fixed

- Documentation complete

**Time Estimate:** 6-8 hours

---

### **DAYS 29-30: Final Testing & Launch**

#### **Day 29: User Acceptance Testing**

**Tasks:**

- [ ] Create test user accounts

- [ ] Test complete user journey (signup â†’ deposit â†’ create match â†’ play â†’ submit result â†’ withdraw)

- [ ] Test dispute resolution flow

- [ ] Test support staff workflows

- [ ] Gather feedback from test users

- [ ] Fix any critical issues

- [ ] Prepare user documentation/help guides

- [ ] Create admin documentation

**Deliverables:**

- User acceptance testing complete

- Critical issues resolved

- Documentation ready

**Time Estimate:** 6-8 hours

---

#### **Day 30: Launch Preparation & Go-Live**

**Tasks:**

- [ ] Final production checks

- [ ] Switch payment gateway to production mode

- [ ] Enable all production features

- [ ] Monitor system health

- [ ] Prepare launch announcement

- [ ] Set up customer support channels

- [ ] Create backup and rollback plan

- [ ] **LAUNCH! ðŸš€**

- [ ] Monitor launch day metrics

- [ ] Address any immediate issues

**Deliverables:**

- **PROJECT COMPLETE!**

- Application live in production

- All PRD requirements met

**Time Estimate:** 8-10 hours

---

## Critical Path Items

These items must be completed in order and cannot be delayed:

1. **Days 1-2:** Database migration and security (blocks everything)

2. **Days 3-6:** Payment integration (critical for user deposits)

3. **Days 7-8:** Evidence upload (required for disputes)

4. **Days 15-21:** API layer (required for mobile app per PRD)

5. **Days 26-27:** Production deployment

---

## Risk Mitigation

### **High-Risk Items:**

1. **Payment Gateway Integration** - May take longer than expected

- *Mitigation:* Start with one provider, add others later

2. **Database Migration** - Data loss risk

- *Mitigation:* Comprehensive backup strategy, test migration multiple times

3. **API Development** - Complex and time-consuming

- *Mitigation:* Use DRF which speeds up development, prioritize core endpoints

4. **Production Deployment** - Infrastructure issues

- *Mitigation:* Set up staging environment first, test deployment process

---

## Success Metrics

By Day 30, the project should have:

âœ… All PRD requirements implemented

âœ… Payment gateway integrated (deposits & withdrawals)

âœ… Evidence upload system functional

âœ… REST API for mobile app support

âœ… PostgreSQL database in production

âœ… Security hardening complete

âœ… Comprehensive logging and monitoring

âœ… Production deployment live

âœ… All critical bugs fixed

---

## Daily Standup Questions

Each day, ask:

1. What did I complete yesterday?

2. What am I working on today?

3. Are there any blockers?

4. Am I on track for the 30-day deadline?

---

## Notes

- **Flexibility:** Some tasks may take longer; adjust subsequent days accordingly

- **Prioritization:** If behind schedule, focus on critical path items first

- **Testing:** Don't skip testing days; bugs found early save time later

- **Documentation:** Update documentation as you go, not at the end

- **Communication:** If using a team, daily standups are essential

---

**Good luck! You've got this! ðŸš€**